## 00_Ringkasan
SYSTEM REQUIREMENT SPECIFICATION & CHECKSHEET
SPBU-GO ¦ Contoh Modul: Login & Hak Akses
Informasi Dokumen | Nilai | Tujuan & Navigasi | Keterangan | Status | Owner | Catatan
Project | SPBU-GO | 01_SRS | Ruang lingkup, aktor, aturan bisnis, dan NFR | Siap review | BA/PO | Baseline kebutuhan
Modul | Login & Hak Akses | 02_Requirements | Daftar fitur dan acceptance criteria | Siap review | BA/PO | Sumber utama requirement
Kode Dokumen | SRS-AUTH-001 | 03_Process_Flow | Alur utama dan exception | Siap review | BA/Dev | Verifikasi end-to-end
Versi | 1 | 04_Data_Model | Entitas, atribut, relasi, dan aturan data | Siap review | Dev/DBA | Dasar ERD
Status Dokumen | Draft untuk Review | 05_Checksheet | Checklist verifikasi requirement | Belum diuji | QA/UAT | Isi hasil dan evidence
Pemilik Dokumen | Section Head / Product Owner | 06_Traceability | Keterlacakan requirement ke flow dan test | Belum diuji | BA/QA | Pantau coverage
Tanggal Dokumen | 2026-09-17 | 07_Panduan_Copy | Cara menyalin kerangka untuk modul lain | Tersedia | Dokumen Owner | Ikuti urutan langkah
RINGKASAN KESIAPAN MODUL
Metrik | Nilai | Gate Persetujuan | PIC | Status | Tanggal | Catatan
Total Requirement | 16 | Business Requirement | Product Owner | Open
Requirement Approved | 0 | Technical Design | Tech Lead | Open
Item Checksheet Pass | 0 | Security Review | Security/IT | Open
Coverage Traceability | 100% | QA Verification | QA Lead | Open
|  | UAT & Go-Live | Business Owner | Open

## 01_SRS
SRS — MODUL LOGIN & HAK AKSES
1. Tujuan | Menjamin hanya pengguna sah yang dapat masuk ke SPBU-GO dan mengakses fungsi sesuai perannya. | Owner | Product Owner
2. Ruang Lingkup | Login dengan username/password, validasi kredensial, pembatasan percobaan, logout, session timeout, reset password, dan role-based access. | In Scope | Web application internal
Out of Scope | Registrasi mandiri, social login, biometric login, dan integrasi SSO pada versi contoh ini. | Dependensi | User master, email service, audit log
3. Aktor | User, Admin Sistem, Product Owner, QA, dan Security Reviewer. | Primary Actor | User
4. Pre-condition | Akun aktif telah tersedia; role sudah terpasang; aplikasi dan database dapat diakses. | Trigger | User membuka halaman login
5. Post-condition | Session aktif dibuat setelah login berhasil; aktivitas login/logout tercatat dalam audit log. | Outcome | Akses sesuai role
6. Asumsi | Password disimpan dalam bentuk hash; email user valid; waktu server tersinkronisasi. | Constraint | Kebijakan keamanan perusahaan
7. Definisi Selesai | Semua requirement prioritas Must lulus, tidak ada defect Critical/High terbuka, evidence tersedia, dan approval lengkap. | Release Gate | Pass
ID | Aturan Bisnis | Parameter Contoh | Verifikasi
BR-AUTH-001 | Akun nonaktif tidak dapat login. | user_status = Active | Negative test
BR-AUTH-002 | Akun dikunci setelah 5 login gagal berturut-turut. | Max attempt = 5 | Boundary test
BR-AUTH-003 | Durasi penguncian otomatis 15 menit atau dibuka Admin. | Lock = 15 menit | Time-based test
BR-AUTH-004 | Session berakhir setelah 30 menit tanpa aktivitas. | Timeout = 30 menit | Idle session test
BR-AUTH-005 | Link reset password berlaku 30 menit dan hanya sekali. | Token TTL = 30 menit | Token reuse test
BR-AUTH-006 | Password baru minimal 8 karakter, memuat huruf besar, kecil, angka, dan simbol. | Complexity policy | Validation test
BR-AUTH-007 | Menu dan aksi ditampilkan berdasarkan permission role aktif. | RBAC | Role matrix test
ID | Kategori NFR | Kebutuhan | Target | Metode Ukur | Priority | Owner | Status
NFR-AUTH-001 | Performance | Respons login normal | ≤ 2 detik pada persentil 95 | Load test 100 concurrent users | Must | Tech Lead | Draft
NFR-AUTH-002 | Availability | Layanan autentikasi tersedia | ≥ 99,5% per bulan | Monitoring uptime | Should | Ops | Draft
NFR-AUTH-003 | Security | Password tidak disimpan sebagai plain text | Hash kuat + salt | Code/config review | Must | Security | Draft
NFR-AUTH-004 | Auditability | Login berhasil/gagal, logout, reset, dan lock tercatat | 100% event wajib | Audit log review | Must | Dev | Draft
NFR-AUTH-005 | Usability | Pesan gagal tidak mengungkap apakah username terdaftar | Generic error message | UI review | Must | UX/QA | Draft
NFR-AUTH-006 | Compatibility | Fungsi berjalan pada browser perusahaan yang didukung | 2 versi mayor terakhir | Cross-browser test | Should | QA | Draft

## 02_Requirements
DAFTAR REQUIREMENT — LOGIN & HAK AKSES
Req ID | Kategori | Fitur | Deskripsi Requirement | Priority | Sumber | Acceptance Criteria | Status | PIC | Evidence/Link
FR-AUTH-001 | Functional | Halaman Login | Sistem menampilkan field username, password, tombol Login, dan tautan Lupa Password. | Must | Product Owner | Semua komponen tampil dan dapat digunakan sesuai desain. | Draft | BA/Dev
FR-AUTH-002 | Functional | Validasi Input | Sistem menolak username atau password kosong. | Must | BR-AUTH | Pesan validasi tampil; request autentikasi tidak dikirim. | Draft | Dev/QA
FR-AUTH-003 | Functional | Autentikasi | Sistem memvalidasi kredensial terhadap user aktif. | Must | Product Owner | Kredensial valid masuk; invalid ditolak dengan pesan generik. | Draft | Dev/QA
FR-AUTH-004 | Security | Failed Attempt | Sistem menghitung percobaan login gagal per akun. | Must | BR-AUTH-002 | Counter bertambah hanya pada kegagalan dan reset setelah login sukses. | Draft | Dev/QA
FR-AUTH-005 | Security | Account Lock | Sistem mengunci akun pada kegagalan kelima berturut-turut. | Must | BR-AUTH-002 | Attempt 1–4 tidak lock; attempt 5 membuat status Locked. | Draft | Dev/QA
FR-AUTH-006 | Functional | Session | Sistem membuat session setelah login berhasil. | Must | Product Owner | Session ID unik dibuat dan user diarahkan ke dashboard. | Draft | Dev/QA
FR-AUTH-007 | Security | Session Timeout | Sistem mengakhiri session setelah 30 menit tidak aktif. | Must | BR-AUTH-004 | Setelah timeout, akses berikutnya kembali ke login. | Draft | Dev/QA
FR-AUTH-008 | Functional | Logout | User dapat mengakhiri session aktif. | Must | Product Owner | Session invalid dan tombol Back tidak membuka halaman terproteksi. | Draft | Dev/QA
FR-AUTH-009 | Functional | Lupa Password | User dapat meminta link reset melalui email terdaftar. | Should | Product Owner | Respons tetap generik; token dikirim untuk akun valid. | Draft | Dev/QA
FR-AUTH-010 | Security | Reset Password | Sistem memvalidasi token dan kebijakan password baru. | Should | BR-AUTH-005/006 | Token valid hanya sekali; password lemah ditolak. | Draft | Dev/QA
FR-AUTH-011 | Authorization | RBAC | Sistem memuat menu dan permission sesuai role user. | Must | BR-AUTH-007 | User hanya melihat dan menjalankan aksi yang diizinkan. | Draft | Dev/QA
FR-AUTH-012 | Audit | Audit Login | Sistem mencatat waktu, user, hasil, IP, dan device info untuk event autentikasi. | Must | NFR-AUTH-004 | Setiap event wajib memiliki timestamp dan result. | Draft | Dev/QA
NFR-AUTH-001 | Performance | Response Time | Respons login memenuhi target performa. | Must | SRS NFR | P95 ≤ 2 detik pada 100 concurrent users. | Draft | Tech Lead/QA
NFR-AUTH-003 | Security | Password Storage | Password disimpan dengan hash dan salt. | Must | SRS NFR | Tidak ada password plain text di DB, log, atau network trace. | Draft | Security/Dev
NFR-AUTH-004 | Audit | Event Coverage | Semua event autentikasi wajib tercatat. | Must | SRS NFR | Login success/fail, lock, reset, logout tercatat 100%. | Draft | Dev/QA
NFR-AUTH-005 | Usability | Secure Message | Pesan error tidak membocorkan keberadaan akun. | Must | SRS NFR | Username salah dan password salah menghasilkan pesan sama. | Draft | UX/QA

## 03_Process_Flow
PROCESS FLOW — LOGIN UTAMA & EXCEPTION
Step | Aktor | Input/Trigger | Proses Sistem | Keputusan | Output | Exception/Recovery | Req Ref | Verified?
1 | User | Buka aplikasi | Tampilkan halaman login | — | Form login tampil | Service unavailable → tampilkan error | FR-AUTH-001 | Belum
2 | User | Username & password | Validasi field wajib | Field lengkap? | Kirim request autentikasi | Kosong → pesan validasi | FR-AUTH-002 | Belum
3 | System | Request autentikasi | Cari user dan cek status | Akun aktif? | Lanjut cek password | Tidak aktif/unknown → pesan generik | FR-AUTH-003 | Belum
4 | System | Password | Verifikasi hash password | Password cocok? | Reset failed counter | Tidak cocok → tambah counter | FR-AUTH-003/004 | Belum
5 | System | Failed counter | Evaluasi jumlah kegagalan | Counter ≥ 5? | Kunci akun | Belum 5 → kembali ke login | FR-AUTH-005 | Belum
6 | System | User valid | Buat session unik | Session berhasil? | Catat login sukses | Gagal → rollback dan pesan error | FR-AUTH-006/012 | Belum
7 | System | Role user | Muat role dan permission | Permission tersedia? | Bentuk menu sesuai role | Tidak ada role → deny access + log | FR-AUTH-011 | Belum
8 | System | Session aktif | Arahkan ke dashboard | — | Dashboard tampil | Route gagal → error page | FR-AUTH-006 | Belum
9 | System | Tidak aktif 30 menit | Cek last activity | Timeout? | Invalidasi session | Aktivitas ada → perpanjang session | FR-AUTH-007 | Belum
10 | User | Klik Logout | Invalidasi session | — | Kembali ke login | Log event gagal → retry async | FR-AUTH-008/012 | Belum
11 | User | Klik Lupa Password | Terima identifier | Akun eligible? | Buat token + kirim email | Selalu tampilkan respons generik | FR-AUTH-009 | Belum
12 | User | Token + password baru | Validasi token dan complexity | Valid? | Ubah password + invalidasi token | Expired/reused/lemah → ditolak | FR-AUTH-010 | Belum

## 04_Data_Model
DATA MODEL / ERD CHECK — MODUL LOGIN & HAK AKSES
Entity | Attribute | Key | Data Type | Nullable | Default | Business Rule | Req Ref | Parent Entity | Relationship | Child Entity | Cardinality | Integrity Rule
users | user_id | PK | UUID | No | Generated | Identifier unik user | FR-AUTH-003 | users | has | user_roles | 1 : N | Delete restricted if active role exists
users | username | UK | VARCHAR(100) | No | — | Unik, case policy ditetapkan | FR-AUTH-003 | roles | assigned through | user_roles | 1 : N | Role must exist
users | email | UK | VARCHAR(255) | No | — | Format email valid | FR-AUTH-009 | users | owns | sessions | 1 : N | Expired session can be purged
users | password_hash | — | VARCHAR(255) | No | — | Tidak menyimpan plain text | NFR-AUTH-003 | users | requests | password_reset_tokens | 1 : N | Only latest valid token usable
users | status | — | VARCHAR(20) | No | Active | Active/Inactive/Locked | FR-AUTH-003/005 | users | generates | audit_logs | 1 : N | Audit retained per policy
users | failed_attempts | — | INT | No | 0 | 0–5, reset setelah sukses | FR-AUTH-004 | roles | grants | permissions | N : M | Implemented via role_permissions
users | locked_until | — | TIMESTAMP | Yes | NULL | Isi saat temporary lock | FR-AUTH-005
roles | role_id | PK | UUID | No | Generated | Identifier unik role | FR-AUTH-011
roles | role_name | UK | VARCHAR(100) | No | — | Nama role unik | FR-AUTH-011 | ERD Verification | Expected | Status | Reviewer | Evidence
user_roles | user_id | PK,FK | UUID | No | — | FK ke users | FR-AUTH-011 | Primary key defined for every entity | Yes | Belum | DBA
user_roles | role_id | PK,FK | UUID | No | — | FK ke roles | FR-AUTH-011 | Foreign key and cardinality match flow | Yes | Belum | DBA/BA
sessions | session_id | PK | UUID | No | Generated | Tidak mudah ditebak | FR-AUTH-006 | Unique constraints prevent duplicate identity | Yes | Belum | DBA
sessions | user_id | FK | UUID | No | — | FK ke users | FR-AUTH-006 | Sensitive values stored securely | Yes | Belum | Security
sessions | expires_at | — | TIMESTAMP | No | — | Sesuai timeout policy | FR-AUTH-007 | Index exists for username/email/token lookup | Yes | Belum | DBA
password_reset_tokens | token_id | PK | UUID | No | Generated | Identifier token | FR-AUTH-010 | Retention/purge rules documented | Yes | Belum | Ops/Security
password_reset_tokens | user_id | FK | UUID | No | — | FK ke users | FR-AUTH-009 | Migration and rollback script reviewed | Yes | Belum | Tech Lead
password_reset_tokens | token_hash | — | VARCHAR(255) | No | — | Token tidak disimpan plain text | FR-AUTH-010
password_reset_tokens | expires_at | — | TIMESTAMP | No | — | Maksimum 30 menit | FR-AUTH-010
audit_logs | audit_id | PK | BIGINT | No | Generated | Identifier event | FR-AUTH-012
audit_logs | user_id | FK | UUID | Yes | NULL | Boleh null untuk unknown user | FR-AUTH-012
audit_logs | event_result | — | VARCHAR(30) | No | — | Success/Fail/Locked/etc. | FR-AUTH-012

## 05_Checksheet
CHECKSHEET VERIFIKASI — LOGIN & HAK AKSES
Check ID | Area | Req Ref | Item yang Diverifikasi | Metode | Expected Result | Hasil | Evidence | Tester/Tanggal | Catatan/Defect ID
CHK-AUTH-001 | Scope | FR-AUTH-001 | Komponen halaman login lengkap | Review + Test | Field dan aksi sesuai SRS | Belum
CHK-AUTH-002 | Flow | FR-AUTH-002 | Validasi field kosong sebelum request | Functional test | Pesan tampil dan request tidak dikirim | Belum
CHK-AUTH-003 | Functional | FR-AUTH-003 | Login dengan kredensial valid | Positive test | Masuk ke dashboard | Belum
CHK-AUTH-004 | Security | FR-AUTH-003 | Login dengan kredensial invalid | Negative test | Ditolak dengan pesan generik | Belum
CHK-AUTH-005 | Boundary | FR-AUTH-004/005 | Percobaan gagal ke-1 sampai ke-5 | Boundary test | Lock tepat pada percobaan ke-5 | Belum
CHK-AUTH-006 | Recovery | FR-AUTH-005 | Akun terbuka setelah 15 menit/Admin unlock | Time/Admin test | User dapat mencoba login kembali | Belum
CHK-AUTH-007 | Session | FR-AUTH-006 | Session unik dibuat setelah login | API/DB test | Session valid terkait user | Belum
CHK-AUTH-008 | Security | FR-AUTH-007 | Idle timeout 30 menit | Time-based test | Session invalid dan redirect login | Belum
CHK-AUTH-009 | Security | FR-AUTH-008 | Back browser setelah logout | Security test | Halaman terproteksi tidak tampil | Belum
CHK-AUTH-010 | Recovery | FR-AUTH-009 | Request reset untuk email valid/invalid | Positive/negative | Respons sama; email hanya untuk akun valid | Belum
CHK-AUTH-011 | Security | FR-AUTH-010 | Token expired dan token reuse | Negative test | Keduanya ditolak | Belum
CHK-AUTH-012 | Validation | FR-AUTH-010 | Kebijakan kompleksitas password | Boundary test | Password lemah ditolak | Belum
CHK-AUTH-013 | Authorization | FR-AUTH-011 | Menu per role | Role matrix test | Menu sesuai permission | Belum
CHK-AUTH-014 | Authorization | FR-AUTH-011 | Akses URL/API tanpa permission | Security test | 403/deny dan tercatat | Belum
CHK-AUTH-015 | Audit | FR-AUTH-012/NFR-AUTH-004 | Event login/logout/reset/lock tercatat | Log review | Seluruh event dan field wajib tersedia | Belum
CHK-AUTH-016 | Data/ERD | NFR-AUTH-003 | Password dan token tidak plain text | DB/code review | Hash + salt; tidak bocor di log | Belum
CHK-AUTH-017 | Performance | NFR-AUTH-001 | Login 100 concurrent users | Load test | P95 ≤ 2 detik | Belum
CHK-AUTH-018 | Usability | NFR-AUTH-005 | Pesan username/password salah identik | UI test | Tidak membocorkan keberadaan akun | Belum
CHK-AUTH-019 | Compatibility | NFR-AUTH-006 | Browser yang didukung | Cross-browser | Lulus 2 versi mayor terakhir | Belum
CHK-AUTH-020 | Error Handling | FR-AUTH-003/006 | DB/auth service unavailable | Resilience test | Pesan aman; tidak ada partial session | Belum
CHK-AUTH-021 | Regression | ALL | Fitur terdampak tetap berjalan | Regression test | Tidak ada regresi Critical/High | Belum
CHK-AUTH-022 | Documentation | ALL | SRS, API, ERD, test evidence konsisten | Document review | Versi dan referensi sinkron | Belum

## 06_Traceability
REQUIREMENT TRACEABILITY MATRIX
Requirement ID | Requirement Ringkas | Flow Step | Data Entity | Check ID | Req Status | Check Result | Coverage
FR-AUTH-001 | Halaman login | 1 | — | CHK-AUTH-001 | Draft | Belum | Covered
FR-AUTH-002 | Validasi input | 2 | — | CHK-AUTH-002 | Draft | Belum | Covered
FR-AUTH-003 | Autentikasi | 3,4 | users | CHK-AUTH-003/004 | Draft | Belum | Covered
FR-AUTH-004 | Failed attempt | 4,5 | users | CHK-AUTH-005 | Draft | Belum | Covered
FR-AUTH-005 | Account lock | 5 | users | CHK-AUTH-005/006 | Draft | Belum | Covered
FR-AUTH-006 | Session | 6,8 | sessions | CHK-AUTH-007/020 | Draft | Belum | Covered
FR-AUTH-007 | Session timeout | 9 | sessions | CHK-AUTH-008 | Draft | Belum | Covered
FR-AUTH-008 | Logout | 10 | sessions/audit_logs | CHK-AUTH-009/015 | Draft | Belum | Covered
FR-AUTH-009 | Lupa password | 11 | password_reset_tokens | CHK-AUTH-010 | Draft | Belum | Covered
FR-AUTH-010 | Reset password | 12 | users/password_reset_tokens | CHK-AUTH-011/012 | Draft | Belum | Covered
FR-AUTH-011 | RBAC | 7 | roles/user_roles | CHK-AUTH-013/014 | Draft | Belum | Covered
FR-AUTH-012 | Audit login | 6,10 | audit_logs | CHK-AUTH-015 | Draft | Belum | Covered
NFR-AUTH-001 | Performance | 2–8 | — | CHK-AUTH-017 | Draft | Belum | Covered
NFR-AUTH-003 | Password storage | 3,4,12 | users/password_reset_tokens | CHK-AUTH-016 | Draft | Belum | Covered
NFR-AUTH-004 | Event coverage | 5,6,10 | audit_logs | CHK-AUTH-015 | Draft | Belum | Covered
NFR-AUTH-005 | Secure message | 3,4,11 | — | CHK-AUTH-004/010/018 | Draft | Belum | Covered

## 07_Panduan_Copy
PANDUAN MENYALIN KERANGKA UNTUK MODUL LAIN
Langkah | Yang Diubah | Lokasi | Output Minimum | Owner | Quality Gate
1 | Duplikat sheet 01–06 | Tab sheet | Satu set dokumen per modul | Document Owner | Nama/kode modul unik
2 | Ubah metadata modul | 00_Ringkasan | Project, modul, kode, versi, owner | PO/BA | Versi terkontrol
3 | Definisikan scope dan aktor | 01_SRS | In/out scope, pre/post condition | PO/BA | Disetujui business
4 | Tulis aturan bisnis & NFR | 01_SRS | Rule terukur dan testable | BA/Architect | Tidak ambigu
5 | Daftar semua requirement | 02_Requirements | ID unik dan acceptance criteria | BA | Semua fitur ter-cover
6 | Petakan happy path dan exception | 03_Process_Flow | Step, decision, output, recovery | BA/Dev | Flow end-to-end
7 | Perbarui ERD/model data | 04_Data_Model | Entity, field, key, relasi, aturan | Dev/DBA | Integritas dan security
8 | Turunkan item verifikasi | 05_Checksheet | Positive, negative, boundary, security | QA | Evidence diwajibkan
9 | Hubungkan semua artefak | 06_Traceability | Req → flow → entity → check | BA/QA | Coverage 100%
10 | Review dan approval | 00_Ringkasan | Business, technical, security, QA, UAT | Semua PIC | Tidak ada Must gagal
Konvensi ID | Pola | Contoh | Wajib? | Catatan | Owner
Functional Requirement | FR-[MODUL]-### | FR-ORDER-001 | Ya | Satu kebutuhan atomik per ID | BA
Non-functional Requirement | NFR-[MODUL]-### | NFR-ORDER-001 | Ya | Target harus terukur | Architect
Business Rule | BR-[MODUL]-### | BR-ORDER-001 | Ya | Referensikan dari requirement | BA
Checksheet | CHK-[MODUL]-### | CHK-ORDER-001 | Ya | Minimal satu check per requirement | QA
Defect | DEF-[MODUL]-### | DEF-ORDER-001 | Jika gagal | Tulis pada kolom catatan | QA